PROJECT PLANNING PHASE  /  ESTIMATION GUIDE

# Planning Logic

Project Title: Auto Ticket Classification Using Flow Designer  |  Date: 3 October 2026  |  Team ID: 6abab5f0ad6b12298106a12a

## How sprint planning works

Sprint: a fixed time period in which a team plans and completes a selected set of work. Epic: a broad outcome broken into smaller stories that can be delivered over multiple sprints. Story: a small piece of user or system value with an acceptance outcome. Story points: a relative estimate of effort, complexity, and uncertainty; they are not hours.

Use the Fibonacci values 1, 2, 3, and 5 for this initial plan. A 5 is the largest estimate in this scale; split larger or uncertain work into smaller stories before committing. The team should estimate collaboratively and refine after learning more.

## Provisional sprint allocations

| Sprint | Epic | Story / task | Points |
| --- | --- | --- | --- |
| Sprint 1 | Discovery & baseline | USN-1 Identify sources/categories/routing paths | 3 |
| Sprint 1 | Discovery & baseline | USN-2 Capture current-state measures | 2 |
| Sprint 1 | Data readiness | USN-3 Review required fields and data gaps | 3 |
| Sprint 1 | Flow foundation | USN-4 Trigger flow and validate ticket fields | 3 |
| Sprint 1 | Classification rules | USN-5 Suggest category for agreed low-risk types | 5 |
| Sprint 2 | Routing & fallback | USN-6 Route eligible records; fallback to triage | 3 |
| Sprint 2 | Agent control & audit | USN-7 Accept/override suggestion and retain audit | 3 |
| Sprint 2 | Requester updates | USN-8 Send confirmation and approved updates | 2 |
| Sprint 2 | Monitoring | USN-9 Report accuracy, reassignments, overrides/errors | 5 |
| Sprint 2 | Pilot readiness | USN-10 Test cases and review pilot results | 3 |

| Sprint | Planned total |
| --- | --- |
| Sprint 1 | 3 + 2 + 3 + 3 + 5 = 16 |
| Sprint 2 | 3 + 3 + 2 + 5 + 3 = 16 |
| Total planned backlog | 16 + 16 = 32 story points |

## Velocity and capacity

Actual velocity formula: total accepted, completed story points divided by the number of completed sprints. Calculate it from completed project sprints and use a rolling average to guide future planning. Do not count unfinished work as completed.

Current project history: no completed sprint data was supplied, so actual velocity is not yet known. The 16 points per sprint shown here is a provisional planning assumption, not measured velocity. At 10 working days per sprint, it implies 1.6 planned points per working day for rough capacity discussion only.

Note on the supplied example The source planning logic calculates 16 points per sprint from a separate data-visualization example. That example is not this project’s delivery history; project estimates above are tailored to ticket classification and must be reviewed by the team.