PROJECT PLANNING PHASE  /  AGILE BASELINE

# Product Backlog and Sprint Planning

Project Title: Auto Ticket Classification Using Flow Designer  |  Date: 3 October 2026  |  Team ID: 6abab5f0ad6b12298106a12a  |  Maximum Marks: 5 Marks

Planning basis: Two proposed 10-working-day sprints, 5-16 October and 19-30 October 2026. Story points use Fibonacci estimates (1, 2, 3, 5, 8). Assign team members and confirm capacity before adopting these dates or commitments.

| Sprint | Functional Requirement (Epic) | Story ID | User Story / Task | Points | Priority | Team member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Discovery & baseline | USN-1 | As a service owner, I can identify ticket sources, high-volume categories, and current routing paths. | 3 | High | TBD |
| Sprint 1 | Discovery & baseline | USN-2 | As a service owner, I can capture baseline assignment accuracy, triage time, reassignment, and volume. | 2 | High | TBD |
| Sprint 1 | Data readiness | USN-3 | As a platform analyst, I can identify required fields and common data-quality gaps for in-scope tickets. | 3 | High | TBD |
| Sprint 1 | Flow foundation | USN-4 | As an administrator, I can trigger a flow for eligible tickets and validate required fields safely. | 3 | High | TBD |
| Sprint 1 | Classification rules | USN-5 | As a triage agent, I can receive rule-based category suggestions for agreed low-risk ticket types. | 5 | High | TBD |
| Sprint 2 | Routing & fallback | USN-6 | As a triage agent, I can route matched tickets and send unmatched or incomplete tickets to human triage. | 3 | High | TBD |
| Sprint 2 | Agent control & audit | USN-7 | As an agent, I can accept or override a suggestion and retain a record of the resulting decision. | 3 | High | TBD |
| Sprint 2 | Requester updates | USN-8 | As a requester, I receive a ticket confirmation and updates through approved existing channels. | 2 | Medium | TBD |
| Sprint 2 | Monitoring | USN-9 | As a service owner, I can review first-assignment accuracy, reassignment, overrides, fallback, and flow errors. | 5 | Medium | TBD |
| Sprint 2 | Pilot readiness | USN-10 | As a project team, we can test representative cases and review pilot results before expanding scope. | 3 | High | TBD |

PROJECT PLANNING PHASE  /  AGILE BASELINE

# Sprint Tracker and Velocity

Project Title: Auto Ticket Classification Using Flow Designer  |  Planned baseline; actual completion and release dates are unreported

## Project Tracker

| Sprint | Planned points | Duration | Start date | Planned end date | Points completed | Actual release date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 16 | 10 working days | 5 Oct 2026 | 16 Oct 2026 | Not reported | Not reported |
| Sprint 2 | 16 | 10 working days | 19 Oct 2026 | 30 Oct 2026 | Not reported | Not reported |

## Velocity and estimation

| Measure | Definition / current value |
| --- | --- |
| Initial planning velocity | 16 story points per sprint (provisional; based on the supplied planning-logic example, not measured project history). |
| Average velocity formula | Total completed story points ÷ number of completed sprints. Recalculate after each sprint using accepted, completed work only. |
| Planning rate | 16 ÷ 10 working days = 1.6 story points per working day (planning assumption). |
| Capacity caveat | Team availability, holidays, dependencies, and actual completion may change capacity. Do not treat planned points as delivered. |

## Burndown Chart

Planned line only. Update remaining work at the end of each working day; plot actual values against the plan.